## Slide 1
XYZ Mobile App
Performance & Release Management Diagnostic
XYZ Company
January 2026

## Slide 2
Our Understanding of Scope
Client seeks a diagnostic-driven assessment to:
• Analyze mobile app latency across Home, Insurance, Spend Track, Quiz & other flows
• Identify root causes behind long load times (6 seconds vs market 2–3 sec benchmark)
• Understand app size inflation (Android: 160MB → 400+MB installed; iOS: 402MB)
• Determine feasibility of moving to a monthly release cycle
• Recommend fixes backed by measurable RCA (no assumptions)
• Provide a North Star performance vision to guide long-term optimization

## Slide 3
Scope of Diagnostic (Mapped to Reference Structure)
Project Start – Pre-Requisite
AB Team:
• Mobile Performance Lead (Flutter)
• Mobile Performance Engineer
• Engineering Manager
Activities:
• Access setup: source code, UAT builds
• Journey & technical walkthrough
• Environment & build readiness confirmation
Diagnostic Pre-Requisite
Inputs Needed From Client:
• Latest production build (APK/IPA)
• Access to Analytics, CMS
• API documentation
• Release pipeline documentation
• Third-party SDK list

## Slide 4
North Star Vision (Benchmarking)
Performance North Star (Industry Benchmarks)
• Primary screen load time: 2 seconds (Market), Current 6 seconds
• Tab-switch latency: 150–250 ms
• App Size Target: 30%–40% reduction
• API latency goal: <150 ms for critical flows
• Rendering frame stability: <16ms per frame
• Release cadence: Predictable Monthly Release Train
Note: These are reference benchmarks only, not commitments until RCA is completed.

## Slide 5
Assumptions
• All access (code, builds, dashboards) will be provided by the client
• Third-party SDK behavior and CMS limitations may restrict optimization
• No changes to backend or CMS unless explicitly included
• RCA outcomes will determine feasibility of performance enhancements
• Recommendations will be measurable and derived from profiling & data
• Any business-driven UI/UX changes are out of scope unless mutually agreed
• Release Management changes are advisory; implementation may require client DevOps involvement

## Slide 6
Architecture & Design Considerations
• Modular, layered architecture assessment
• API sequencing, dependency mapping
• Asynchronous vs synchronous rendering optimization
• Third-party SDK footprint & load behavior
• Lazy-loading feasibility
• Asset compression & caching strategies
• Separation of concerns for future scalability
• Release governance & branching strategy review

## Slide 7
Proposed Diagnostic Architecture View
Includes review of:
• App frontend architecture (Flutter)
• API Gateway interactions
• CMS-driven modules
• Third-party SDK integrations (Fly, MarTech, Payments, Firebase)
• Performance telemetry flows
• Release pipeline & CI/CD workflows

## Slide 8
Our Approach (Diagnostic) – Week 0 to Week 4
Week 0 – Setup & Access
• Access provisioning
• Environment setup
• Build validation
Week 1 – Profiling & Analysis
• Load-time benchmarking
• API call mapping & latency analysis
• App size/composition breakdown
• Cache & render-path profiling
Week 2 – RCA & Observations
• Root-cause identification (H/M/L)
• Fixable vs dependency-driven issues
• Third-party SDK constraints
• Release pipeline maturity assessment
Week 3 – Discussions
• Joint walkthrough of findings
• Validation with client teams
• Feasibility confirmation
• Monthly release model alignment
Week 4 – Final Report
• North Star vs Achievable Targets
• Performance uplift range
• Recommended fixes
• Execution Plan & Sizing

## Slide 9
Team Structure
Role
Count
Responsibility
Mobile Performance Lead
1
Profiling, rendering, app load optimization
Mobile Engineer
2
Code analysis, architecture assessment
Solution Architect
1
Engineering Manager, Program Management, Architecture
Total Team: 3 Members (Diagnostic Phase)

## Slide 10
Gantt Timeline (Week-Level)
W0
W1
W2
W3
W4
Week 0 – Setup & Access
Week 1 – Profiling & Analysis
Week 2 – RCA & Observations
Week 3 – Discussions & Verifications
Week 4 – Final Report

## Slide 11
Commercial Structure
Diagnostic Phase (4 Weeks)
• Fixed fee (based on 4–5 resources for 1 month equivalent)
• Covers analysis, RCA, reporting, release advisory
Execution Phase
• To be estimated based on diagnostic output
• Dependent on size of fixable items

## Slide 12
Risks & Dependencies
• Third-party SDK limitations
• CMS payload constraints
• Launch-time API dependencies
• Device fragmentation & low-RAM behavior
• Release process maturity
• Environment availability

## Slide 13
Final Outcome
A North-Star aligned, data-backed, feasible performance roadmap including:
• What can be improved
• What cannot be improved
• Expected uplift range
• Team & timeline for execution
• Monthly release readiness assessment