## Slide 1
XYZ Mobile App
Performance & Release Management Diagnostic
XYZ Company
January 2026

## Slide 2
Our Understanding of Scope
Client seeks a comprehensive diagnostic-driven assessment:
Analyze
Mobile app latency across Home, Insurance, Spend Track, Quiz & other key user flows
Identify
Root causes behind long load times (6 sec current vs 2-3 sec market benchmark)
Understand
App size inflation patterns (Android: 160MB→400MB+; iOS: 402MB)
Determine
Feasibility of moving to a monthly release cycle
Recommend
Fixes backed by measurable Root Cause Analysis - no assumptions
Provide
North Star performance vision to guide long-term optimization strategy

## Slide 3
Scope of Diagnostic
🔧 AB Team Resources
▸ Mobile Performance Lead
Flutter Expert
▸ Mobile Performance Engineer
Code Analysis
▸ Engineering Manager
Program Management
📋 Key Activities
• Access setup: source code, UAT builds
• Journey & technical walkthrough
• Environment & build readiness confirmation
📦 Inputs From Client
📱 Latest production build (APK/IPA)
📊 Access to Analytics, CMS
📑 API documentation
🚀 Release pipeline documentation
🔌 Third-party SDK list

## Slide 4
North Star Vision
🎯 Industry Benchmarks & Target Goals
⚡
Screen Load Time
2 sec
Target (Target)
vs 6 sec Current
✓ 60% improvement
🔄
Tab-Switch Latency
150-250
ms (Target)
vs 500+ ms
✓ Visual feedback
💾
App Size Reduction
30-40%
Target (Target)
vs Growing Current
✓ User retention
🌐
API Latency
<150
ms critical (Target)
vs 300+ ms
✓ Core flows
🎬
Frame Stability
<16
ms/frame (Target)
vs Janky Current
✓ Smooth UX
📅
Release Cadence
Monthly
Predictable (Target)
vs Ad-hoc Current
✓ Consistent
📌 Note: These are reference benchmarks only. Actual commitments determined post-RCA.

## Slide 5
Key Assumptions
1
Client Access
All access (code, builds, dashboards) will be provided by the client in a timely manner
2
SDK Limitations
Third-party SDK behavior and CMS limitations may restrict optimization scope
3
Backend Scope
No changes to backend or CMS unless explicitly included in the engagement
4
RCA-Driven
RCA outcomes will determine feasibility - not all items may be fixable
5
Data-Driven
Recommendations will be measurable and derived from profiling & telemetry data
6
UX Stability
Business-driven UI/UX changes out of scope unless mutually agreed
7
Advisory Role
Release Management changes are advisory; client DevOps owns implementation

## Slide 6
Architecture & Design Focus
Architecture Assessment
Modular Layers
API Sequencing
Async Rendering
SDK Footprint
Lazy Loading
Asset Cache
🎯 Plus: Separation of concerns, Release governance, Branching strategy review

## Slide 7
Proposed Diagnostic Architecture
📱 App Frontend
Flutter architecture deep-dive
🌐 API Gateway
Interaction patterns & latency
📦 CMS Modules
Content-driven module analysis
🔌 SDK Integrations
Fly, MarTech, Payments, Firebase
📊 Telemetry
Performance data flows
🚀 CI/CD Pipeline
Release workflows & automation

## Slide 8
Diagnostic Approach: Week 0-4
W0
Setup
• Access provision
• Environment
• Build validation
W1
Profiling
• Load benchmarks
• API mapping
• Size breakdown
• Cache profiling
W2
RCA
• Root-cause ID
• Fixable analysis
• SDK constraints
• Pipeline review
W3
Validation
• Joint walkthrough
• Team validation
• Feasibility check
• Release model
W4
Report
• Target alignment
• Uplift range
• Fixes list
• Execution plan

## Slide 9
Expert Team Structure
👨‍💻
Mobile Performance Lead
Flutter Expert
1
Profiling, rendering, optimization
👩‍💻
Mobile Engineers
Code Analysts
2
Code analysis, architecture assessment
🎯
Solution Architect
Strategic Lead
1
Engineering Mgmt, Program Mgmt, Architecture
🚀 Total Team: 3 Members (Diagnostic Phase)

## Slide 10
Project Timeline (Gantt View)
W0
W1
W2
W3
W4
Setup & Access
Profiling & Analysis
RCA & Observations
Discussions & Validation
Final Report
Kickoff
Data Ready
Findings
Validation
Delivery

## Slide 11
Investment Structure
🔍 DIAGNOSTIC PHASE
⏱ 4 WEEKS
✓ Fixed fee structure
✓ 4-5 resources (1 month FTE)
✓ Comprehensive analysis
✓ Root cause documentation
✓ Release advisory report
🚀 EXECUTION PHASE
📋 TBD
⏳ Estimation post-diagnostic
⏳ Dependent on fixable scope
⏳ Detailed sprint planning
⏳ Resource allocation
⏳ Timeline confirmation

## Slide 12
Risk Factors & Dependencies
⚠️
Third-Party SDKs
External SDK behavior may limit optimization options
📡
CMS Constraints
Content Management System payload restrictions
⏰
API Dependencies
Launch-time API calls blocking user experience
📱
Device Fragmentation
Low-RAM device behavior variations
🚀
Release Maturity
Current release process capabilities
🔧
Environment Access
UAT/Production environment availability

## Slide 13
🎯 Final Deliverables
Your comprehensive, data-backed performance roadmap
✅
Improvement Plan
What CAN be improved with estimated impact
❌
Constraints Doc
What CANNOT be improved & why (SDK/CMS limits)
📈
Uplift Range
Expected performance gains per optimization area
👥
Execution Plan
Team structure & timeline for implementation
📅
Release Readiness
Monthly release train feasibility assessment
🚀 North Star Aligned • Data-Backed • Feasible & Actionable